## Sprint1
|  | Pending |  | Incomplete |  | Completed
Name | Date
|  | 2019-11-13 | Status | 2019-11-14 | Status | 2019-11-15 | Status | 2019-11-16 | Status | 2019-11-18 | Status | 2019-11-19 | Status | 2019-11-20 | Status | 2019-11-21 | Status | 2019-11-22 | Status
Jason |  | OTP Generation |  | OTP Generation |  | Email Generation |  | Email Generation |  | Module Design |  | Project Discussion and Sprint Planning |  | User Stories |  | Bean class creation |  | checking flowof first two forms
Jasmin |  | Table Connection |  | Table Connection |  | Home page Discussion |  | Home page Designing |  | Home page Designing |  | Home page Designing |  | HTML forms |  | HTML forms |  | validation for two pages
Mushtari |  | Database Schema |  | Class diagram and Flowchart |  | Database Flow |  | HTML Forms |  | Home page Designing |  | Home page Designing |  | HTML forms |  | HTML forms |  | validation for all form pages
Tiru Ajan |  | Table Connection |  | Header and Footer |  | Header and Footer |  | Form Design Discussion |  | Form Design Discussion |  | Creating Jsp pages |  | Creating Jsp pages |  | Login page and registration page |  | Login page and registration page
Athira |  | Table Creation |  | Table Creation |  | Logo Creation |  | Logo Creation |  | Form Flow |  | Creating Jsp pages |  | Creating Jsp pages |  | Login page and registration page |  | Login page and registration page

## Sprint2
| Pending |  | Incomplete |  | Completed
Name
| 2019-11-23 | Status | 2019-11-24 | Status | 2019-11-25 | Status
Jason | Admin Controller |  | Admin Controller |  | Admin Controller
Jasmin | Admin Controller |  | Admin Controller, FlowChart |  | User Id and Account No. Generation
Mushtari | Remaining Form Designs |  | FlowChart and Presentation |  | Mail and Login Templates
Tiru Ajan | Jsp pages for Remaining forms |  | Remaining Form Designs |  | Mail and Login Templates
Athira | Jsp pages for Remaining forms |  | Remaining User Controllers |  | Mail Check